## Sheet1
Work Breakdown Structure
Issue No. | Associated Webpage | Due Date | Associated Tasks | Priority | Risk | Responsible | Category
| Login Page | 2023-09-30 | DB Structure |  | Intial Setup Problems | Kumai | General
|  | 2023-10-04 | Initial Setup |  |  | All
|  | 2023-10-08 | Static Front-end |  |  | Manal & Steven
|  | 2023-10-15 | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
| Registration | 2023-10-15 | Static Front-end |  |  | Manal
|  | 2023-10-22 | Dynamic Front-end |  |  | Gabriel
|  | 2023-10-15 | SQL & DB Communication |  |  | Kumai
| Property Search | 2023-10-22 | Static Front-end |  |  | Manal & Steven
|  | 2023-10-29 | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  | 2023-10-22 | SQL & DB Communication |  |  | Kumai
| Administrator Dashboard | 2023-10-15 | Static Front-end |  |  | Steven | Admin
|  | 2023-10-22 | Dynamic Front-end |  |  | Leen & Yousef
|  | 2023-10-15 | SQL & DB Communication |  |  | Kumai
| Property Listing Management |  | Static Front-end |  |  | Manal & Steven | Broker
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Offer Submission & Offer Management |  | Static Front-end |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Visit Mangement |  | Static Front-end |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Broker Profile |  | Static Front-end |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Visit Request |  | Static Front-end |  |  | Manal & Steven | Client
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Favorites Page |  | Static Front-end |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai
| Client Profile |  | Static Front-end |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  | Kumai