## Sheet1
Work Breakdown Structure - Sprint 2 Planning
Associated Webpage | Issue No. | Due Date | Associated Tasks | Story Points | Priority | Risk | Responsible | Category
Login Page |  | 2023-09-30 | DB Structure | 3 | 1 | Forgeting Important parameters or making an unvalid structure | Kumai | General
|  | 2023-10-04 | Initial Setup | 2 | 2 | incompatibility Setup problems on different operating systems (MAC/Windows) | All
|  | 2023-10-06 | Static Front-end | 1 | 3 | Runtime bugs. | Manal & Steven
|  | 2023-10-07 | Dynamic Front-end | 1 | 3 |  | Leen, Gabriel & Yousef
Registration |  |  | Static Front-end | 2 |  | Relatively simple page. The only risk is a non-maintenable code due to lack of experience. (Still early stage of the project) | Manal & Steven
|  |  | Dynamic Front-end | 1 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 1 |  |  | Kumai
Property Search |  | 2023-10-13 | Static Front-end | 5 | 6 | The is our first complex page. We might run into runtime bugs, filtering complexity. Non-friendly user interface. Time delays. | Manal & Steven
|  | 2023-10-20 | Dynamic Front-end | 5 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 2 |  |  | Kumai
Administrator Dashboard |  | 2023-10-08 | Static Front-end | 3 | 4 | Runtime problems. Complex CRUD logic. (What will happen if the admin decides to delete brokers who have published properties?) | Manal & Steven | Admin
|  | 2023-10-09 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 2 |  |  | Kumai
Property Listing Management |  | 2023-10-09 | Static Front-end | 3 | 5 | The logic can conflicts with the admin CRUD operations or the visit mangement CRUD operations. | Manal & Steven | Broker
|  | 2023-10-11 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 2 |  |  | Kumai
Offer Submission & Offer Management |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  |  | Kumai
Visit Mangement |  | 2023-10-22 | Static Front-end | 3 | 8 | The logic can conflicts with the admin CRUD operations or the property listing mangement CRUD operations. | Manal & Steven
|  | 2023-10-25 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 2 |  |  | Kumai
Broker Profile |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  |  | Kumai
Visit Request |  | 2023-10-20 | Static Front-end | 2 | 7 | This a simple form to fill up by the user. The only risk is runtime errors | Manal & Steven | Client
|  | 2023-10-22 | Dynamic Front-end | 2 |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication | 1 |  |  | Kumai
Favorites Page |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  |  | Kumai
Client Profile |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  | SQL & DB Communication |  |  |  | Kumai