## Sheet1
Task | Notes | Responsible | Time Spent
Sprint 1
Reading the project requirements and brainstorming individually and as a Team | We have read the provided documents by the professor to have a general idea about the project. We have also discussed how we are going to approach the project and what technologies we were going to choose. | All Team Members | 3 Hours
Initializing GitHub Repository | Creating a GitHub repository and adding all Team members. | Gabriel | 10 minutes
User Stories | Writing all user stories based on the project description. | Kumai | 30mins
Discussing Rules and responsibilities and Sprint 1 Requirements | We have assigned the rules and responsibilities based on the previous experience of the team members and also based on individual interests. | Everyone | 1 hour
Writing Sprint 1 PDF Document | Summarizing all the discussed ideas in a well formated PDF. | Kumai | 3 hours
Creating GitHub Issues | Creating an issue for every task on the planning Excel Sheet. | Youssef | 1 hour
Creating the Wiki page | Creating a wiki page on GitHub and refrencing the excel planning sheet on it. | Kumai & Yousef | 30mins
Creating an Excel planning sheet | Creating a planning sheet to divide tasks and assign due dates. We had difficulties to plan for the next sprit because very minimum information were provided about sprint 2. The task has been assigned two days before the first sprint due date. | Kumai | 1 hour
Finalizing Sprint 1 | Having a team call to go over all the required documents and making sure nothing is missing | Kumai & Yousef | 1 hour
Writing the meeting minutes | Writing the meeting minutes for most of the meetings | Manal | 30 minutes
Sprint 2