## Sheet1
Work Breakdown Structure - Sprint 3 Planning
Associated Webpage | Progress | Issue No. | Due Date | Associated Tasks | Story Points | Priority | Risk | Responsible | Category
Login Page | DONE | 3 | 2023-09-30 | DB Structure | 3 | 1 | Forgeting Important parameters or making an unvalid structure | Kumai | General
| DONE | 4 | 2023-10-04 | Initial Setup | 2 | 2 | incompatibility Setup problems on different operating systems (MAC/Windows) | All
| DONE | 5 | 2023-10-06 | Static Front-end | 1 | 3 | Runtime bugs. | Manal & Steven
| DONE | 6 | 2023-10-07 | Dynamic Front-end | 1 | 3 |  | Leen, Gabriel & Yousef
Registration | DONE | 1 | 2023-11-01 | Static Front-end | 2 | low | Relatively simple page. The only risk is a non-maintenable code due to lack of experience. (Still early stage of the project) | Manal & Steven
|  | 2 | 2023-11-03 | Dynamic Front-end | 1 | low |  | Leen, Gabriel & Yousef
|  | 3 | 2023-11-01 | SQL & DB Communication | 1 | low |  | Kumai
Property Search | DONE (Can be improved) | 7 | 2023-10-13 | Static Front-end | 5 | LOW | The is our first complex page. We might run into runtime bugs, filtering complexity. Non-friendly user interface. Time delays. | Manal & Steven
| DONE (Can be improved) | 8 | 2023-10-20 | Dynamic Front-end | 5 |  |  | Leen, Gabriel & Yousef
| DONE | 9 | 2023-10-13 | SQL & DB Communication | 2 |  |  | Kumai
DONE
Administrator Dashboard | DONE (Can be improved) | 10 | 2023-10-08 | Static Front-end | 3 | LOW | Runtime problems. Complex CRUD logic. (What will happen if the admin decides to delete brokers who have published properties?) | Manal & Steven | Admin
| DONE (Can be improved) | 11 | 2023-10-09 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
| DONE | d | 2023-10-08 | SQL & DB Communication | 2 |  |  | Kumai
13
Property Listing Management | DONE (Can be improved) | 14 | 2023-10-09 | Static Front-end | 3 | LOW | The logic can conflicts with the admin CRUD operations or the visit mangement CRUD operations. | Manal & Steven | Broker
| DONE (Can be improved) | 15 | 2023-10-11 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
| DONE (Can be improved) | 16 | 2023-10-09 | SQL & DB Communication | 2 |  |  | Kumai
Offer Submission & Offer Management | To be during sprint 3 |  | 2023-11-04 | Static Front-end | 2 | HIGH | We only have one week for this sprint. It might be difficult to make a good quality page. | Manal & Steven
|  |  | 2023-11-06 | Offer submission js | 1 |  |  | Leen, Gabriel & Yousef
|  |  | 2023-11-04 | SQL & DB Communication | 1 |  |  | Kumai
|  |  | 2023-11-06 | Offer Management js
Visit Mangement | DONE | 17 | 2023-10-22 | Static Front-end | 3 | LOW | The logic can conflicts with the admin CRUD operations or the property listing mangement CRUD operations. | Manal & Steven
| DONE | 18 | 2023-10-25 | Dynamic Front-end | 3 |  |  | Leen, Gabriel & Yousef
| DONE | 19 | 2023-10-22 | SQL & DB Communication | 2 |  |  | Kumai
Broker Profile | To be during sprint 3 |  | 2023-11-04 | Static Front-end | 2 | MEDIUM | We only have one week for this sprint. It might be difficult to make a good quality page. | Manal & Steven
|  |  | 2023-11-06 | Dynamic Front-end | 1 |  |  | Leen, Gabriel & Yousef
|  |  | 2023-11-04 | SQL & DB Communication | 1 |  |  | Kumai
Visit Request | DONE | 20 | 2023-10-20 | Static Front-end | 2 | LOW | This a simple form to fill up by the user. The only risk is runtime errors | Manal & Steven | Client
| DONE | 21 | 2023-10-22 | Dynamic Front-end | 2 |  |  | Leen, Gabriel & Yousef
| DONE | 21 | 2023-10-20 | SQL & DB Communication | 1 |  |  | Kumai
Favorites Page |  |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  |  | SQL & DB Communication |  |  |  | Kumai
Client Profile |  |  |  | Static Front-end |  |  |  | Manal & Steven
|  |  |  | Dynamic Front-end |  |  |  | Leen, Gabriel & Yousef
|  |  |  | SQL & DB Communication |  |  |  | Kumai