## Sheet1
Task | Notes | Responsible | Time Spent
Sprint 1
Reading the project requirements and brainstorming individually and as a Team | We have read the provided documents by the professor to have a general idea about the project. We have also discussed how we are going to approach the project and what technologies we were going to choose. | All Team Members | 3 Hours
Initializing GitHub Repository | Creating a GitHub repository and adding all Team members. | Gabriel | 10 minutes
User Stories | Writing all user stories based on the project description. | Kumai | 30mins
Discussing Rules and responsibilities and Sprint 1 Requirements | We have assigned the rules and responsibilities based on the previous experience of the team members and also based on individual interests. | Everyone | 1 hour
Writing Sprint 1 PDF Document | Summarizing all the discussed ideas in a well formated PDF. | Kumai | 3 hours
Creating GitHub Issues | Creating an issue for every task on the planning Excel Sheet. | Youssef | 1 hour
Creating the Wiki page | Creating a wiki page on GitHub and refrencing the excel planning sheet on it. | Kumai & Yousef | 30mins
Creating an Excel planning sheet | Creating a planning sheet to divide tasks and assign due dates. We had difficulties to plan for the next sprit because very minimum information were provided about sprint 2. The task has been assigned two days before the first sprint due date. | Kumai | 1 hour
Finalizing Sprint 1 | Having a team call to go over all the required documents and making sure nothing is missing | Kumai & Yousef | 1 hour
Writing the meeting minutes | Writing the meeting minutes for most of the meetings | Manal | 30 minutes
Sprint 2
Admin page, connection to db, adding and removing brokers from website. Working on editing broker | Contacted kumai a lot | Gabriel and Kumai | 9h
Worked on home page (indedx) , listings page, nav bar, the broker page, the functionality with a calandar on the broker page, the HTMLa dn CSS of these pages, the search page, implimented a slideshow function on the homepage (javascript), added a details page for each listing with a calculator functionality for the listings, HTML and CSS of the Login page. Contact and about-us page | Contacted kumai a lot | Steven Zrihen | 15hr
Creating Sql querries and associated JavaScript functions for frontend-backend communications | I had communicated with Gabriel and Yousef to make sure the needed data, filer parameters, and all database related functions are available for the pages development. | Steven and Kumai | 8h
Working on the property search front-end back-end integration and improving UI | There are still work to be done to improve the user interface. For now, the user can easily search for properties by the area, maximum price, and if it is for sale or for rent. | Gabriel and Kumai | 5h
Initializing CI/CD Pipeline on GitHub and making a basic testing architecture for the project | It is difficult to perform test cases when the whole project is locally hosted. The test cases are done locally and the work perfectly. However, they do not work on GitHub since there is no way to connect to the local database. Hence, I have setup hard coded data for now, but this can be easily changed once a better database enviornment is set. | Kumai | 8h
Setting up test cases for the project | There is only one php file to be tested. Other files are all JavaScript files. However, there are too many sql querries related functions that need to be tested. | Kumai | 5h
Peer reviewing and support | Helping other teams with the setup and debugging. | Kumai | 6h
Acceptance test | wrote 2 acceptance tests | Manal | 1 hour
Sprint 3 Planning | Put due dates and assigned people to tasks | Manal | 1 hour
User Stories | wrote 3 user strories for sprint 3 features (admin, broker, client) | Leen | 1 hour
Meeting Minutes | Writing meeting minutes | Leen | 1 hour