## Sheet1
Task | Responsible | Time Spent
Sprint 1
Reading the project requirements and brainstorming individually and as a Team | All Team Members | 3 Hours
Initializing GitHub Repository | Gabriel | 10 minutes
Discussing Rules and responsibilities and Sprint 1 Requirements | Everyone | 1 hour
Writing Sprint 1 PDF Document | Kumai | 3 hours
Finalizing Sprint 1 | Everyone | 1 hour
Writing the meeting minutes | Manal | 30 minutes
Sprint 2